## Initial Plan
Color Coding |  |  | Completed |  |  |  | FALL 2021 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Date | 2021-09-14 | 2021-09-21 | 2021-09-28 | 2021-10-05 | 2021-10-12 | 2021-10-19 | 2021-10-26 | 2021-11-02 | 2021-11-09 | 2021-11-16 | 2021-11-23 | 2021-11-30 | 2021-12-07 | 2021-12-14 | 2021-12-21
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | ALL | 2021-09-14 | 2021-09-16 | 100%
| Confirm Project Team Roles |  | ALL | 2021-09-17 | 2021-09-21 | 100%
| Develop two business cases |  | Shazia, Praneta | 2021-09-17 | 2021-09-21 | 100%
| Develop Project Initiation Document (PID) |  | ALL | 2021-09-21 | 2021-10-04 | 100%
| Produce initial Project Plan, RACI |  | ALL | 2021-09-28 | 2021-10-04 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Praneta Kasbe | 2021-10-05 | 2021-10-11 | 100%
| Produce Context Diagram, Define System Interfaces |  | George Hidalgo | 2021-10-05 | 2021-10-11 | 100%
| Define Business Requirements |  | Praneta Kasbe | 2021-10-12 | 2021-10-18 | 100%
| Agree to System Requirements types |  | All | 2021-10-12 | 2021-10-18 | 100%
| Define Functional Decomposition |  | All | 2021-10-12 | 2021-10-18 | 100%
| Produce RCT document |  | George Hidalgo | 2021-10-12 | 2021-10-18 | 100%
| Decide which features to implement this semester |  | All | 2021-10-12 | 2021-10-18 | 100%
| Produce analysis diagrams (UML, DFD) |  | George Hidalgo | 2021-10-19 | 2021-10-25 | 100%
| Define functional requirements (User Stories) |  | George Hidalgo | 2021-10-19 | 2021-10-25 | 100%
| Update Project Plan with additional requirements tasks |  | Shazia Khan | 2021-10-19 | 2021-10-25 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | DataFlow Diagram(Physical) |  | George Hidalgo | 2021-11-02 | 2021-11-08 | 100%
| Database Design (ERD, Table spec) |  | Sanket bagul | 2021-11-02 | 2021-11-08 | 100%
| Architecture design (2 diagrams) |  | Xinhao Huang | 2021-11-09 | 2021-11-15 | 100%
| System Interface Design |  | Xinhao Huang | 2021-11-08 | 2021-11-15 | 100%
| User interface design |  | Xinhao Huang | 2021-11-08 | 2021-11-15 | 100%
| Account Authentication | Functionality Detailed Design | Xinhao Huang | 2021-11-08 | 2021-11-15 | 100%
| Account Summary | Functionality Detailed Design | Xinhao Huang | 2021-11-08 | 2021-11-15 | 100%
| Customer Support | Functionality Detailed Design | Xinhao Huang | 2021-11-08 | 2021-11-15 | 100%
| Browse Products | Functionality Detailed Design | Xinhao Huang | 2021-11-08 | 2021-11-15 | 100%
| Make Payment | Functionality Detailed Design | Xinhao Huang | 2021-11-08 | 2021-11-15 | 100%
| Upload Products | Functionality Detailed Design | Xinhao Huang | 2021-11-08 | 2021-11-15 | 100%
| Submit rating | Functionality Detailed Design | Xinhao Huang | 2021-11-08 | 2021-11-15 | 100%
| Post Review | Functionality Detailed Design | Xinhao Huang | 2021-11-08 | 2021-11-15 | 100%
| Et-In-Internal Entitlements | Functionality Detailed Design | Xinhao Huang | 2021-11-08 | 2021-11-15 | 100%
| Et-Ex-External Entitilements | Functionality Detailed Design | Xinhao Huang | 2021-11-08 | 2021-11-15 | 100%
| PT- Product Type | Functionality Detailed Design | Xinhao Huang | 2021-11-08 | 2021-11-15 | 100%
| FV Field Validation | Functionality Detailed Design | Xinhao Huang | 2021-11-08 | 2021-11-15 | 100%
| Student Table | Populate test data | Sanket Bagul, Along Zhang | 2021-11-14 | 2021-11-30 | 100%
| Product Table | Populate test data | Sanket Bagul, Along Zhang | 2021-11-14 | 2021-11-30 | 100%
| Order Table | Populate test data | Sanket Bagul, Along Zhang | 2021-11-14 | 2021-11-30 | 100%
| Payment_Info Table | Populate test data | Sanket Bagul, Along Zhang | 2021-11-14 | 2021-11-30 | 100%
| Upload Product Table | Populate test data | Sanket Bagul, Along Zhang | 2021-11-14 | 2021-11-30 | 100%
| Rating Table | Populate test data | Sanket Bagul, Along Zhang | 2021-11-14 | 2021-11-30 | 100%
| Feedback Table | Populate test data | Sanket Bagul, Along Zhang | 2021-11-14 | 2021-11-30 | 100%
| Contact_Us Table | Populate test data | Sanket Bagul, Along Zhang | 2021-11-14 | 2021-11-30 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | Account Authentication | GUI | Xinhao Huang | 2021-11-16 | 2021-11-22 | 100%
| Account Summary | GUI | Xinhao Huang | 2021-11-16 | 2021-11-22 | 100%
| Customer Support | GUI | Xinhao Huang | 2021-11-16 | 2021-11-22 | 100%
| Browse Products | GUI | Xinhao Huang | 2021-11-16 | 2021-11-22 | 40%
| Make Payment | GUI | Xinhao Huang | 2021-11-16 | 2021-11-22 | 40%
| Upload Products | GUI | Xinhao Huang | 2021-11-16 | 2021-11-22 | 40%
| Submit rating | GUI | Xinhao Huang | 2021-11-16 | 2021-11-22 | 40%
| Post Review | GUI | Xinhao Huang | 2021-11-16 | 2021-11-22 | 40%
| Et-In-Internal Entitlements | GUI | Xinhao Huang | 2021-11-16 | 2021-11-22 | 40%
| Et-Ex-External Entitilements | GUI | Xinhao Huang | 2021-11-16 | 2021-11-22 | 40%
| PT- Product Type | GUI | Xinhao Huang | 2021-11-16 | 2021-11-22 | 40%
| FV Field Validation | GUI | Xinhao Huang | 2021-11-16 | 2021-11-22 | 40%
| Account Management | Table specifications (Data Dictionary) | Sanket Bagul | 2021-11-16 | 2021-11-22 | 100%
|  | Establish Code repository in GitHub | Xinhao, Shazia | 2021-11-16 | 2021-11-22 | 100%
|  | Coding & Implemenation | Xinhao Huang | 2021-11-23 | 2021-11-29 | 100%
| Buy/Sell Products | Table specifications (Data Dictionary) | Sanket Bagul | 2021-11-16 | 2021-11-22 | 40%
|  | Establish Code repository in GitHub | Xinhao, Shazia | 2021-11-16 | 2021-11-22 | 40%
|  | Coding & Implemenation | Xinhao Huang | 2021-11-23 | 2021-11-29 | 40%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document |  | Saahiil Meswaanii | 2021-11-30 | 2021-12-06 | 100%
| Evaluate Features to be Tested |  | Along Zhang | 2021-11-30 | 2021-12-06 | 100%
| Account Authentication | Design Test Cases | Saahiil Meswaanii | 2021-11-30 | 2021-12-06 | 100%
|  | Execute Test Cases | Along Zhang | 2021-11-30 | 2021-12-06 | 100%
|  | Anaylze Test Results | ALL | 2021-11-30 | 2021-12-06 | 100%
| Account Summary | Design Test Cases | Saahiil Meswaanii | 2021-11-30 | 2021-12-06 | 100%
|  | Execute Test Cases | Along Zhang | 2021-11-30 | 2021-12-06 | 100%
|  | Anaylze Test Results | ALL | 2021-11-30 | 2021-12-06 | 100%
| Customer Support | Design Test Cases | Saahiil Meswaanii | 2021-11-30 | 2021-12-06 | 0%
|  | Execute Test Cases | Along Zhang | 2021-11-30 | 2021-12-06 | 0%
|  | Anaylze Test Results | ALL | 2021-11-30 | 2021-12-06 | 0%
| Browse Products | Design Test Cases | Saahiil Meswaanii | 2021-11-30 | 2021-12-06 | 0%
|  | Execute Test Cases | Along Zhang | 2021-11-30 | 2021-12-06 | 0%
|  | Anaylze Test Results | ALL | 2021-11-30 | 2021-12-06 | 0%
| Make Payment | Design Test Cases | Saahiil Meswaanii | 2021-11-30 | 2021-12-06 | 0%
|  | Execute Test Cases | Along Zhang | 2021-11-30 | 2021-12-06 | 0%
|  | Anaylze Test Results | ALL | 2021-11-30 | 2021-12-06 | 0%
| Upload Products | Design Test Cases | Saahiil Meswaanii | 2021-11-30 | 2021-12-06 | 0%
|  | Execute Test Cases | Along Zhang | 2021-11-30 | 2021-12-06 | 0%
|  | Anaylze Test Results | ALL | 2021-11-30 | 2021-12-06 | 0%
| Submit Rating | Design Test Cases | Saahiil Meswaanii | 2021-11-30 | 2021-12-06 | 0%
|  | Execute Test Cases | Along Zhang | 2021-11-30 | 2021-12-06 | 0%
|  | Anaylze Test Results | ALL | 2021-11-30 | 2021-12-06 | 0%
| Post Review | Design Test Cases | Saahiil Meswaanii | 2021-11-30 | 2021-12-06 | 0%
|  | Execute Test Cases | Along Zhang | 2021-11-30 | 2021-12-06 | 0%
|  | Anaylze Test Results | ALL | 2021-11-30 | 2021-12-06 | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | ALL | 2021-12-14 | 2021-12-20 | 100%